## Sheet1
| Deliverable |  |  | Responsible | Draft | Next Draft | Status | Comments
Administration
1 | Deliverables Outline |  |  | Shreve/Blantz/Levine | 2000-08-31 | 2000-10-06 |  | This Document
2 | Agenda for Tokyo |  |  | Shreve/McLure | 2000-10-07
3 | Develop BPCC paragraph for TA document |  |  | Levine | 2000-11-10
4 | Joint Delivery Team Web Site |  |  | Hayes
5 | Issues List |  |  | Seaburg | 2000-09-29 |  |  | On going
Analysis/Methodology
6 | Matrix of Representation Classes |  |  | Probert | 2000-08-18 | Tokyo | delivered 10/3/00
7 | Industry Analysis Results |  |  | Heilig | 2000-10-16
8 | Registration Authority Procedures Document |  |  | Probert | 2000-11-10
9 | Integrate CC Methodology with BP Methodology |  |  | Hayes/Bryan | 2000-10-09 |  |  | Primary Responsibility Clark/Sugamata
10 | Align with outside methodologies |  |  | Clark |  |  |  | On going
11 | Guidelines for applying methodology end to end |  |  | Hayes | 2000-09-19 | 2000-10-15 |  | Includes core processes, patterns
12 | Catalog of Core Processes |  |  | Hayes | 2000-11-06 | 2001-02-12 |  | List first, specifications later
13 | Patterns |  |  | Clark
14 |  | Commercial transaction level (N90) |  | Clark
15 |  | eCommerce Patterns |  | Haugen
16 |  | Pattern validation |  | Domain teams
17 | Business process specification templat |  |  | Hayes | 2000-10-06
18 | Top-to-bottom example |  |  | Najmi/Clark/Probert
19 | Update CC entry form |  |  | Bryan | 2000-08-31
Context/Metamodel
20 | ebXML metamodel |  |  | Riemer/Gregory
21 |  | Actual ebXML metamodel |  | Clark
22 |  | Metamodel specification/UML profile |  | Clark | 2000-10-15
23 |  |  | Incorporate context refinement | Gregory | 2000-10-15 | 2000-11-10
24 |  |  | TPA Alignment | Clark/Hayes
25 |  | Scenarios for use of metamodel |  | Riemer
26 |  | Metamodel example |  | Clark
27 | Core Component Context
28 |  | Matrix |  | Kadlek | 2000-08-31 | 2000-11-10
29 |  | Value Classifications |  | Kadlek | 2000-11-10 | 2001-02-01
30 |  | Rules |  | Adcock | 2000-10-11 |  |  | OCL rules become reference
31 |  | Extensibility |  | Adcock | 2000-10-04
Domain Teams
32 | Proof of Concept Proposal |  |  | Riemer/Handleman | 2000-09-15
33 | XML format for storage in registry |  |  | Lonjon | 2000-09-20
34 | Example |  |  | Heilig/Handleman | 2000-09-15
35 |  | Core Process Model
36 |  | Automotive Extended Process Model
37 |  | Core Business Messages
38 |  | Automotive Extended Business Messages